## Sheet1
SR. NO. | TASK NAME | Expected Timeline | Days | WORK EXPERIENCE | REMARK
1 | AWS Static Web Hosting | 2 Days | Day 1 | Follow the all steps for hosting a static website in AWS
2 | AWS Static Web Hosting | 2 Days | Day2 | I prepare the documentation of this project
3 | Upload the image with Lambda Function | 5 Days | Day3 | Research for this project and collect the resources
4 | Upload the image with Lambda Function | 4 Days | Day 4 | I tried to start the project but unexpectedly, it gave some errors | Due to the error, I did'nt make it
5 | Upload the image with Lambda Function | 4 Days | Day 5 | Half of the project is completed
6 | Upload the image with Lambda Function | 4 Days | Day 6 | The whole project is completed with lots of efforts
7 | Integrated Grafana with Linux | 3 Days | Day 7 | Collect the resources from the you tube and google
8 | Integrated Grafana with Linux | 3 Days | Day 8 | After collecting the resources and understanding the concept move ahead the project | Due to the error, I unable to make it
9 | Integrated Grafana with Linux | 3 Days | Day 9 | The Project is completed